## Hoja1
integrantes del equipo | [6 empty] | duracion del proyecto en meses
Nombres | Iniciales | rol | Pago por hora
ISC. Efraín Morales Arredondo | EMA | DIRECTOR | 200 |  |  |  | 4
Ana Paulina Lopez Cazares | APLC | ALUMNO | 120
Miguel Angel Gonzalez Gallegos | MAGG | ALUMNO
.
Horas laboradas
| Fecha |  | APLC | MAGG | EMA | Total equipo
Planeacion | 15/08/22 | 31/08/22 | 18.98 | 28.05 | 1.96 | 47.03
Requerimientos y analisis | 2022-01-09 | 29/09/22 | 44 | 52.42 | 3 | 96.42
| 30/09/22 | 25/10/22 | 54 | 49.67 | 7.2 | 103.67
Diseño
| 26/10/22 | 18/11/22 | 74.5 | 74.27 | 6.6 | 148.77
TT | 15/08/22 | 18/11/2022 | 191.48 | 204.41 | 18.76 | 395.89
Costo de equipo
Pertenesiente | Costo del equipo | Depeseacion por mes |  | Depreseacion total
APLC | 20000 | 1666.6667 |  | 6666.6667
MAGG | 7500 | 625 |  | 2500
MAGG | 10000 | 833.3333 |  | 1666.6667
Total | 37500 | 3125 |  | 10833.3333
Recursos humanos alumnos
| 15/08/22 - 31/08/22 |  | 1/9/2022 - 29/09/22 |  | 30/09/22 - 25/10/22 |  | 26/10/22 - 18/11/22 | Tiempo total por persona | Ganancia por person
APLC | 18.98 |  | 44 |  | 54 |  | 74.5 | 191.48 | 22977.6
MAGG | 28.05 |  | 52.42 |  | 49.67 |  | 74.27 | 204.41 | 24529.2
tiempo total por quincena en horas | 47.03 |  | 96.42 |  | 103.67 |  | 148.77 | 395.89 | 47506.8
Ganancia por quincena | 5643.6 |  | 11570.4 |  | 12440.4 |  | 17852.4 | 47506.8
Recursos humanos director
EMA | 1.96 |  | 3 |  | 7.2 |  | 6.6 | 18.76 | 3752
Ganancia por quincena | 392 |  | 600 |  | 1440 |  | 1320 | 3752
Ganancia total por quincena | 6035.6 |  | 12170.4 |  | 13880.4 |  | 19172.4 | 51258.8
Total de recursos humanos: | [8 empty] | 51258.8
Activos fijos
| Costo mensual |  | Costo del proyecto |  | Total
Recursos | APLC | MAGG | APLC | MAGG
Agua | 50 | 0 | 200 | 0 | 200
Luz | 210 | 0 | 840 | 0 | 840
Internet | 133 | 0 | 532 | 0 | 532
Renta | 0 | 1100 | 0 | 4400 | 4400
Total | 393 | 1100 | 1572 | 4400 | 5972
Estimacion del proyecto
Integrantes | EMA | APLC | MAGG | Total
Recursos humanos (50%) | 3752 | 22977.6 | 24529.2 | 51258.8
Costos fijos | 0 | 1572 | 4400 | 5972
Imprevistos (10%) | 375.2 | 2297.76 | 2452.92 | 5125.88
subtotal | 4127.2 | 26847.36 | 31382.12 | 62356.68
Ganancia (inflacion + premio al riesgo) (20%) | 825.44 | 5369.472 | 6276.424 | 12471.336
Total | 4952.64 | 32216.832 | 37658.544 | 74828.016
Note on F26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Se consiguió a inicios de octubre